## Slide 1
ROAD CONNECTIVITY SECTOR 1 PROJECT – ADB GRANT No. 0051-NEP(SF) GOVERNMENT OF NEPAL, MINISTRY OF PHYSICAL PLANNING AND WORKS DEPARTMENT OF ROADS
CONTRACT RCSP / ICB / SB / 01
SUNKOSHI BRIDGE AND APPROACHES
SEMINAR
“CONSENSUS ON CONTRACT COMPLETION”
MMM GROUP Canada formerly N.D. Lea Inc. in association with CEMAT Consultants (Pvt.) Ltd. Nepal, Soil Test (Pvt.) Ltd. Nepal, Total Management Services (TMS) Nepal

## Slide 2
STAGE 1
INFORMATION STAGE

## Slide 3
FORMAT
THIS IS A WORKING SEMINAR
NO SPEECHES
MINIMUM FORMALITIES

## Slide 4
INTRODUCTIONS
THOSE PRESENT ON BEHALF OF THE
EMPLOYER
CONTRACTOR
ENGINEER
ARE REQUESTED TO INTRODUCE THEMSELVES

## Slide 5
PURPOSE OF THE SEMINAR
PRIMARY PURPOSE
TO REACH CONSENSUS ON
THE BEST OPTIONS FOR CONTRACT COMPLETION
SECONDARY PURPOSE
TO AGREE A TIMEBOUND ACTION PLAN
TO ACHIEVE THE CONSENSUS

## Slide 6
STRUCTURE OF THE SEMINAR
THE SEMINAR HAS SIX STAGES
STAGE 1 - INFORMATION STAGE
STAGE 2 - DESIGN PRESENTATION
STAGE 3 - OPTION DEVELOPMENT
STAGE 4 - EVALUATION
STAGE 5 - CONSENSUS
STAGE 6 - ACTION PLANNING

## Slide 7
CURRENT STATUS OF THE CONTRACT
THE CONTRACT IS APPROXIMATELY 54% COMPLETE
THE CONTRACT IS OUT OF TIME
THE CONTRACT (AS CURRENTLY DESIGNED) CANNOT NOW BE COMPLETED WITHIN THE LOAN PERIOD TIMEFRAME
THIS ADVERSELY AFFECTS THE PERFORMANCE EVALUATION OF THE OVERALL RCSP PROJECT
THE SEMINAR IS DESIGNED TO SEEK A SOLUTION
IT IS NOT PROPOSED THAT THE REASONS FOR THE CURRENT UNFORTUNATE SITUATION BE DISCUSSED AT THIS SEMINAR

## Slide 8
NON-NEGOTIABLE CONDITIONS IN VALUE ENGINEERING EVALUATION
BRIDGE DESIGN MUST BE IN ACCORDANCE WITH APPROPRIATE CODES
ALL CONSTRUCTION ELEMENTS MUST BE VERIFIABLE UNDER QA PROCEDURES

## Slide 9
STAGE 2
DESIGN PRESENTATION
Presented by
BIHARI LAL BALLA – RESIDENT ENGINEER

## Slide 10
STAGE 3
OPTION DEVELOPMENT
DISCUSSION OF DESIGN MODIFICATION OPTIONS
TEA BREAK
AGREEMENT OF ACCEPTABLE MODIFICATIONS

## Slide 11
STAGE 4
EVALUATION
OPTIONS &
CONSIDERATION OF GAINS / OFFSETS
BY EACH CONTRACT PARTY

## Slide 12
OPTIONS 1
ESSENTIALLY THERE ARE 2 OPTIONS
OPTION 1
CONTINUE WITH THE CONTRACT FOR A FURTHER LOW WATER SEASON AND BUILD THE BRIDGE AS ORIGINALLY DESIGNED

## Slide 13
OPTIONS 2
OPTION 2
VARY THE CONTRACT TO INCORPORATE AGREED DESIGN MODIFICATIONS AND COMPLETE THE BRIDGE BY END 2012

## Slide 14
ASSESSMENT
OPTION 1
FAILS TO COMPLETE THE BRIDGE WITHIN THE STIPULATED LOAN PERIOD
OPTION 2
IS THE PREFERRED OPTION OF THE 2 PARTIES TO THE CONTRACT

## Slide 15
ANALYSIS
OPTION 2
REQUIRES ANALYSIS OF THE GAINS / OFFSETS OF EACH CONTRACT PARTY
THIS IS A VALUE ENGINEERING ANALYSIS
In accordance with GCC Clause 13.2 Value Engineering Sub-Clause (c)

## Slide 16
For information:
GCC CLAUSE 13.2 VALUE ENGINEERING
Sub-Clause (c) (ii)
STATES
The reduction (if any) in the value to the Employer of the varied works, taking account of any reductions in quality, anticipated life or operational efficiencies

## Slide 17
EMPLOYER – GAINS
EARLIEST POSSIBLE COMPLETION
EMPLOYER – OFFSETS
LESS ROBUST FACTORS OF SAFETY

## Slide 18
CONTRACTOR – GAINS
REDUCTION OF DIFFICULT ACTIVITIES (SINKING)
CONTRACTOR – OFFSETS
SUGGESTED OFFSETS ARE

## Slide 19
SUGGESTED OFFSETS
IN ACCORDANCE WITH GCC CLAUSE 13.2 VALUE ENGINEERING Sub-Clause (c)
CONTRACTOR WAIVES ALL COST CLAIMS RELATED TO TIME PROLONGATION AND ALLEGED UNFORSEEABLE PHYSICAL CONDITIONS

## Slide 20
EVALUATION
EMPLOYER ACCEPTS
CONTRACTOR WAIVING ALL COST CLAIMS RELATED TO TIME PROLONGATION AND ALLEGED UNFORSEEABLE PHYSICAL CONDITIONS
AS BEING REASONABLE OFFSET FOR LESS ROBUST SAFETY FACTORS (BUT WITHIN THE CODE)
THE EMPLOYER AGREES NOT TO IMPOSE PENALTIES
FOR LATE COMPLETION PROVIDED BRIDGE
IS COMPLETED BY END DECEMBER 2012

## Slide 21
STAGE 5
CONSENSUS
Consensus to be defined by
VISHNU P. SHRESTHA – DEPUTY TEAM LEADER

## Slide 22
CONSENSUS TO COVER
ACCEPTABLE DESIGN MODIFICATIONS
OFFSETS AGREED BY CONTRACTOR

## Slide 23
STAGE 6
ACTION PLANNING
EXECUTION OF THE CONSENSUS
WILL REQUIRE 3 STEPS

## Slide 24
STEP 1
CONTRACTOR
Present agreed Design Modification under GCC Clause 13.2 Value Engineering
Undertake responsibility for design in accordance with GCC Clause 13.2 (a)
Provide revised Construction Program
Step 1 to be complete by ?

## Slide 25
STEP 2
ENGINEER
Prepare Variation Order under GCC Clause 13.3 Variation Procedure
Covering Design Modification, “Offsets” agreed by Contractor and revised Program
Obtain Contractor’s signed agreement
Step 2 to be complete by ?

## Slide 26
STEP 3
EMPLOYER
Approval of Variation Order
Step 3 to be complete by ?

## Slide 27
SUMMARY & CLOSE
THANK YOU – ALL PARTICIPANTS
HOPEFULLY WE NOW HAVE A ROUTE TO SUCCESSFUL COMPLETION
LUNCH IS THE NEXT ACTIVITY